## Timelines
Digtal Project Plan | Key
Workshop
Agency
Client Review
Client: {Insert Client Name} |  | Client Production
Version: {Insert Version Number} |  | Completed
Date: {Insert Date} |  | Holidays
Timeframe | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
Dates | Week 1: Jan 1st; Holidays Week 2: Jan 8th
Workshop | bar: Week 1
#1- Planning:
Project plan prepared | bar: Holidays Week 2 to Holidays Week 4
Client review | bar: Holidays Week 5 to Holidays Week 6
Amends | bar: Holidays Week 7
Client sign-off | bar: Holidays Week 7
#2- Strategy
UX strategy prepared and sitemap prepared
Client review
Amends
Client sign-off
#3- Wireframing
Wireframes produced for each template
Client review
Amends
Client sign-off
#4- Design
Homepage Design Concepts Produced
Homepage Client review
Rest of templates designed
Client review
Amends
Sign-off
Packaging and supply of design assets
#5- Content production
Review of content on current site
Creation of new content needed
Client Review
Amends
Sign-off
#6- Development
Production and supply of brief to developers
Theme development and integration with the CMS
#7- User Acceptance Testing and bug fixing
Agency / Developer Testing
Bug fixing
Rest of stakeholders testing
Snag list supplied by the client
Bug fixing
#8- Content and SEO migration
Content migration and freeze
Redirect map prepared and rolled out
#9- Client sign off
All UAT bugs fixed and approval granted to push the files to the live hosting environment.
#10- Go live
Domain DNS settings changed to point to the new website server.